## Scorecard
DecisionMesh — GPT Recommendations Scorecard
Area | Score | Status | Key Gap
── PLATFORM ─────────────────────────────────────────────────────────────
AI Decision Governance Pipeline | ✅ 100% | DONE | Complete: Intent→Policy→Model→Eval→Audit
Policy Engine | ✅ 95% | DONE | Complete. Simplify UI for business users (no-code)
AI Audit Trail | ✅ 100% | DONE | audit_log + governance_ledger + intent_events all live
Human Review Queue | ⚠️ 30% | PARTIAL | No /review-queue page. Backend concepts exist but no UI
AI Evaluation (quality/drift/cost) | ✅ 90% | DONE | Quality score, hallucination risk, drift dashboard all live
── INTENT LIBRARY ───────────────────────────────────────────────────────
Tier 1 Intents (Fraud/Lending/Compliance) | ✅ 100% | DONE | All 30 Tier 1 intents seeded and accessible
Tier 2-5 Intents (40+ intents) | ✅ 100% | DONE | All seeded. Need to deprioritize in UI
Universal Templates (6 types) | ⚠️ 40% | PARTIAL | Supported technically. No dedicated UI cards in Playground
Curated 40-intent UI view | ❌ 0% | PENDING | Currently shows all 264. Need tiered/featured view
── DEMOS & SALES ────────────────────────────────────────────────────────
Demo 1: Fraud Governance | ⚠️ 60% | PARTIAL | SmartRenderer shows risk. Missing human review step
Demo 2: Loan Approval Governance | ⚠️ 40% | PARTIAL | Intent exists. No human approval UI. No scripted flow
Demo 3: Compliance Audit | ⚠️ 50% | PARTIAL | Intents exist. Decision trace UI not built. No compliance page
10-slide deck | ❌ 0% | PENDING | Not created
Demo video (5 min) | ❌ 0% | PENDING | Not recorded
Outreach list (100 fintechs) | ❌ 0% | PENDING | Not built
── INFRASTRUCTURE (ALREADY STRONG) ─────────────────────────────────────
Production deployment (Hetzner + Cloudflare) | ✅ 100% | DONE | dm-api + dm-api-staging + Caddy + Prometheus + Grafana
Auth (Zitadel OIDC) | ✅ 100% | DONE | PKCE flow; JWT validation; tenant provisioning on login
Payments (Stripe/Razorpay) | ❌ 5% | BLOCKED | Code complete. Blocked on GST registration
GitHub Org Migration | ✅ 100% | DONE | thirupala → decimeshi; all images; CI/CD updated
── REVENUE STATUS ───────────────────────────────────────────────────────
Demos booked | ❌ 0 demos | PENDING | No outreach started yet
Pilot customers | ❌ 0 pilots | PENDING | Platform ready; no customers
Paid ARR | ❌ $0 | BLOCKED | Blocked on GST → Stripe
── OVERALL SCORE ────────────────────────────────────────────────────────
Platform Engineering | ✅ 88% | DONE | Excellent. Minor gaps: human review UI, decision trace UI
GTM / Sales Readiness | ❌ 15% | PENDING | Critical gap. No demos, no deck, no outreach, no customers
Revenue Enablement | ⚠️ 25% | PARTIAL | GST blocking payments; need 3 demos and pilot closes

## GPT Recommendations Gap
DecisionMesh — GPT Recommendations vs Implementation Gap Analysis
GPT Recommendation | Category | Status | What's Built | What's Missing / Next Step | Priority
── PRODUCT POSITIONING ──────────────────────────────────────────────────────────────────────────
Don't sell: AI Gateway / Intent Catalog — sell: AI Governance & Compliance Control Plane | Positioning | DONE | Landing page says 'AI Decision Control Plane'; tagline 'Every AI decision governed, audited, compliant'; deployed at decimeshi.com | — Website messaging already aligned; ensure sales deck matches | P0
Tagline: 'Every AI decision governed, audited, compliant' | Positioning | DONE | Tagline on decimeshi.com matches exactly | — | P0
── PHASE 1 MVP: 5 CAPABILITIES ──────────────────────────────────────────────────────────────────
MVP Cap 1: AI Decision Governance — Intent → Policy → Model → Eval → Decision Record → Audit | Core Platform | DONE | Full pipeline: Intent submission → PlannerService → Policy evaluation → LLM adapter → OutputQualityScorerService → Audit trail. ControlPlaneOrchestrator.java implements full chain | — | P0
MVP Cap 2: AI Policy Engine — YAML-like rules (cost cap, confidence threshold) | Policy Engine | DONE | PolicyEngine with PRE/POST execution phases; COST_CAP, RISK_THRESHOLD, RATE_LIMIT rule types; PolicyBuilder UI; enforcement modes: LOG_ONLY/SOFT_BLOCK/HARD_BLOCK | Business-user DSL editor (no-code rule builder) — currently JSON-based. Simplify UI for non-technical users | P1
MVP Cap 3: AI Audit Trail — intent, model, prompt, decision, reasoning, policyVersion, timestamp | Audit | DONE | audit_log table; governance_ledger; lifecycle_audit; intent_events (append-only, immutable triggers); AuditLog.jsx page; all fields stored | — | P0
MVP Cap 4: Human Review Queue — AI → Review Queue → Human Approves → Audit Updated | Human Review | PARTIAL | review_queue concept exists in governance. IntentCentricSLAGuard can flag for review. audit_log records human actions | No dedicated Human Review Queue UI page. Need: /review-queue page listing pending approvals; approve/reject buttons; audit update on action | P0
MVP Cap 5: AI Evaluation — track accuracy, cost, latency, hallucination, compliance | Analytics | DONE | OutputQualityScorerService: quality score, hallucination risk, faithfulness, completeness. Drift dashboard. Cost analytics. Prometheus + Grafana metrics. All shown in UI | — | P0
── GPT SAYS: IGNORE THESE FOR NOW ──────────────────────────────────────────────────────────────
❌ Marketplace — do NOT build | Scope Control | DONE | No marketplace built. Intent Library is internal templates, not a marketplace | Keep as internal — do not add public marketplace | P0
❌ Multi-agent governance — do NOT build | Scope Control | DONE | Single-agent execution only. No multi-agent orchestration built | — | P0
❌ 264 expanded intents — do NOT build more | Scope Control | PARTIAL | 264 fintech intents seeded in intent_library table. GPT says this is too many for the UI | Curate to 40-60 visible intents in UI. Show Tier 1 (Fraud/Lending/Compliance) first. Hide rest as 'advanced' | P1
❌ Healthcare/Telecom/Insurance/Custom DSL — do NOT build | Scope Control | DONE | Fintech focus only. No healthcare or telecom intents | Insurance tier-5 exists in library — deprioritize in UI | P1
❌ 15MB JSON catalogs — do NOT build | Scope Control | DONE | Not built | — | P0
── FIRST SELLABLE PACKAGE: GOVERNANCE STARTER ──────────────────────────────────────────────────
Target: Fintechs, NBFCs, Banks | GTM | DONE | 264 fintech intents cover PAYMENTS, LENDING, FRAUD, COMPLIANCE — right target market | Outreach list of 100 fintechs not yet built. Start with Hyderabad/Bangalore fintech clusters | P0
Pricing: Starter $2-5k/mo ¦ Growth $10-20k/mo ¦ Enterprise $50k+/yr | Pricing | PARTIAL | Pricing model exists in decisionmesh_pricing.pdf. Credit tiers: Free/Hobby/Builder/Pro/Enterprise | Credit-based pricing ≠ enterprise SaaS pricing. Add USD/month pricing page alongside credit tiers for enterprise deals | P1
Demo 1: Fraud Detection — show policy, model, risk score, human review, audit | Demo | PARTIAL | Playground has fraud_detection intent with SmartResponseRenderer (risk gauge, APPROVE/DECLINE badge, risk factors). Policy engine live. | Human review step missing from demo flow. Create scripted demo data set with pre-loaded fraud scenario | P0
Demo 2: Loan Approval — AI rec, policy validation, human approval, audit trail | Demo | PARTIAL | approve_loan intent exists in library. Policy engine validates. Audit trail complete. | Human approval UI missing. No 'loan approval workflow' page that shows end-to-end flow for demo | P0
Demo 3: Compliance — RBI controls, DPDPA, data lineage, decision traceability | Demo | PARTIAL | Compliance intents: kyc_verification, screen_sanctions, check_pep, conduct_edd. audit_log + governance_ledger exists. Decision traces table populated. | No dedicated Compliance Dashboard page. Decision trace UI not built (backend ready). Need single page showing: active RBI/DPDPA policies → decision → audit record | P0
── INTENT MARKETPLACE TEMPLATES (TIER 1-5) ────────────────────────────────────────────────────
Tier 1 Fraud & Risk: detect_fraud_transaction, score_transaction_risk, detect_aml (10 intents) | Intent Library | DONE | All 10 Tier 1 fraud intents seeded: detect_fraud_transaction, score_transaction_risk, flag_suspicious_transaction, detect_account_takeover, verify_device, monitor_velocity_fraud, assess_geo_risk, detect_identity_theft, detect_aml, identify_mule_account | — | P0
Tier 1 Lending: approve_loan, calculate_credit_score, predict_default (10 intents) | Intent Library | DONE | All 10 lending intents seeded: approve_loan, reject_loan, assess_borrower_risk, calculate_credit_score, predict_default, verify_income, verify_employment, adjust_credit_limit, recommend_loan, disburse_loan | — | P0
Tier 1 Compliance: kyc_verification, screen_sanctions, check_pep, conduct_edd (10 intents) | Intent Library | DONE | All 10 compliance intents seeded: kyc_verification, screen_sanctions, check_pep, conduct_edd, verify_beneficial_owner, monitor_suspicious_activity, validate_regulation, generate_compliance_report, audit_trail, assess_country_risk | — | P0
Tier 2-5: Payments, AP/AR, Treasury, Investment, Insurance (40 intents) | Intent Library | DONE | All tier 2-5 intents seeded across PAYMENTS(25), AP_AR(29), TREASURY(20), INVESTMENTS(21), INSURANCE(10) categories | Deprioritize in UI — show Tier 1 first; Tier 2-5 as 'Advanced' | P1
Universal Templates: classification, recommendation, decision, risk_assessment, compliance, extraction | Intent Library | PARTIAL | Generic intentType field supports any string. Playground allows custom types. No dedicated universal template cards in UI | Add 6 universal template quick-select cards in Playground/Library: Classification, Recommendation, Decision, Risk Assessment, Compliance, Extraction | P1
── UI: SHOW 40-60 CURATED INTENTS (NOT ALL 264) ───────────────────────────────────────────────
Show grouped: Fraud & Risk (4), Lending (3), Compliance (3), Payments (4), Treasury (2), Insurance (2), Universal (6) | UI/UX | PENDING | Intent Library currently shows all 264. No tiered/curated view implemented | Implement tiered view: Featured (Tier 1, ~30 intents) visible by default. 'Advanced Library' toggle shows all 264. Group by vertical with icon cards | P0
User journey: Choose Intent → Modify → Adjust Policies → Select Model → Configure Human Review → Submit | User Journey | PARTIAL | Choose → Modify → Submit works (Playground). Policy config exists. Model tier selector exists. | Missing: 'Configure Human Review' step in Playground. Add toggle: 'Require human approval for this execution' with reviewer email field | P0
── GPT SAYS: BUILD THIS WEEK ───────────────────────────────────────────────────────────────────
Landing page | Marketing | DONE | decimeshi.com live on Cloudflare Pages with product messaging | Review GPT's recommended positioning — update hero copy if needed | P0
Governance dashboard | UI | PARTIAL | Dashboard.jsx exists with KPI cards, intent list, credit balance, cost charts | Missing: Governance-specific view. Add 'Governance' tab showing: active policies count, blocked intents today, human review queue count, compliance score | P0
Policy engine | Core | DONE | PolicyEngine fully implemented and deployed. PRE/POST execution. Builder UI. | — | P0
Audit trail | Core | DONE | audit_log + governance_ledger + lifecycle_audit all live. AuditLog.jsx page. | — | P0
Fraud demo (scripted) | Sales | PARTIAL | Playground has SmartResponseRenderer for fraud. Risk gauge and factors show. | Need: pre-loaded demo tenant with fraud scenario data. Script the 15-min demo flow. Record demo video. | P0
Loan demo (scripted) | Sales | PARTIAL | approve_loan intent exists. Policy validation works. | Need: scripted loan demo with human review step. Missing human review queue. | P0
10-slide investor/customer deck | Sales | PENDING | Not built | CREATE: 10-slide deck covering problem, architecture, demo screenshots, use cases, ROI, pricing | P0
LinkedIn content | Marketing | PENDING | Not started | CREATE: 5 LinkedIn posts — governance story, fraud demo screenshot, compliance screenshot, customer problem, pricing | P0
Demo video (5 min) | Marketing | PENDING | Not recorded | RECORD: Loom/OBS walkthrough — fraud governance demo, loan approval, compliance audit | P0
Outreach list (100 fintechs) | Sales | PENDING | Not built | BUILD: LinkedIn Sales Navigator or manual list — Hyderabad/Bangalore fintechs, NBFCs, payment aggregators. Target: 20-200 employee companies | P0
── SUCCESS METRICS (MEASURE THESE NOT INTENT COUNT) ────────────────────────────────────────────
Demos booked (target: 10 in 30 days) | Metrics | PENDING | 0 demos booked | Start outreach immediately — email + LinkedIn + warm intros | P0
Pilot customers (target: 3 in 60 days) | Metrics | PENDING | 0 pilot customers | Offer free 90-day pilot to first 3 fintechs that demo | P0
Paid customers / ARR | Metrics | PENDING | $0 ARR (payments blocked on GST) | GST → current account → Stripe live → first invoice | P0
3 pilot customers using Fraud / Loan / Compliance governance | Revenue Goal | PENDING | Platform ready. No customers yet. | This is the 60-day milestone. Everything else is secondary. | P0

## 30-Day Action Plan
DecisionMesh — Revenue-Focused 30-Day Action Plan
# | Task | Details | Owner | Deadline | Status | Priority
WEEK 1 — DEMO & DECK (Days 1-7)
1 | Human Review Queue UI | Build /review-queue page: list pending AI decisions; Approve/Reject buttons; audit update on action. Required for loan and fraud demos. | Dev | Day 3 | PENDING | P0
2 | Curated Intent UI (40 intents) | Show Tier 1 intents (Fraud/Lending/Compliance) by default. 'Advanced Library' toggle for all 264. Group with icons and descriptions. | Dev | Day 4 | PENDING | P0
3 | Governance Dashboard Tab | Add Governance tab to Dashboard: active policies count, blocked intents today, human review queue count, compliance score gauge. | Dev | Day 4 | PENDING | P0
4 | Universal Templates in Playground | Add 6 quick-select cards: Classification, Recommendation, Decision, Risk Assessment, Compliance, Extraction. | Dev | Day 5 | PENDING | P1
5 | 10-Slide Deck | Slide 1: Problem. Slide 2: Solution. Slide 3: Architecture. Slide 4: Demo screenshots. Slide 5: Use cases. Slide 6: ROI. Slide 7: Pricing. Slide 8: Traction. Slide 9: Team. Slide 10: CTA. | Thiru | Day 5 | PENDING | P0
6 | Script 3 demos | Write step-by-step demo scripts: (1) Fraud governance 15-min. (2) Loan approval 15-min. (3) Compliance audit 15-min. Create demo tenant with seed data. | Thiru | Day 6 | PENDING | P0
7 | Record 5-min demo video | Loom/OBS recording of fraud governance demo. Publish to YouTube unlisted. Add to decimeshi.com. | Thiru | Day 7 | PENDING | P0
WEEK 2 — MARKETING & CONTENT (Days 8-14)
8 | Update decimeshi.com messaging | Hero: 'AI Governance for Regulated Decisions'. Sub: 'Every AI decision governed, audited, compliant.' Add fraud/loan/compliance sections. Remove generic AI gateway language. | Thiru | Day 9 | PENDING | P0
9 | 5 LinkedIn posts scheduled | Post 1: The governance problem. Post 2: Fraud detection demo screenshot. Post 3: Loan approval governance. Post 4: DPDPA/RBI compliance. Post 5: Pricing and pilot offer. | Thiru | Day 12 | PENDING | P0
10 | Decision Trace UI | Build Decision Trace panel in IntentDetail (backend complete): adapter reason, policy summary, cost rationale. Critical for compliance demo. | Dev | Day 12 | PENDING | P0
11 | Compliance Dashboard page | Single page showing: active RBI/DPDPA policies, recent compliance intents, decision lineage, audit export button. | Dev | Day 14 | PENDING | P1
WEEK 3 — OUTREACH (Days 15-21)
12 | Build outreach list (100 fintechs) | LinkedIn Sales Nav or manual. Focus: Hyderabad/Bangalore fintechs, NBFCs, payment aggregators, digital lenders. 20-200 employees. Decision maker: CTO/CPO/CDO. | Thiru | Day 17 | PENDING | P0
13 | Send 100 outreach messages | Email/LinkedIn DM. Template: 'We built AI governance for RBI-regulated decisions. Can I show you a 15-min demo?' Include demo video link. | Thiru | Day 21 | PENDING | P0
14 | Internship hire for QA/GTM | Hire 1-2 interns via Internshala for QA execution (test case register ready) and outreach support. DECIMESHI is registered — can offer internships. | Thiru | Day 15 | PENDING | P1
15 | GST follow-up | Follow up on GST clarification letter submitted June 2026. GST → current account → Stripe live keys. | Thiru | Day 17 | IN PROGRESS | P0
WEEK 4 — CLOSE PILOTS (Days 22-30)
16 | Run 10+ demos | Target: 10 demos in week 4. Use scripted flow. Record objections. Iterate pitch. | Thiru | Day 28 | PENDING | P0
17 | Close 3 pilot customers | Offer: free 90-day pilot with white-glove onboarding. Ask: 1 fraud use case, 1 loan use case, or 1 compliance use case. | Thiru | Day 30 | PENDING | P0
18 | Fix DB-001 (V2 migration) | adapter_profile_versions missing adapter_id. execution_records ON CONFLICT fix. Write V2__fix_schema_issues.sql and deploy. | Dev | Day 3 | PENDING | P0
19 | Fix Stripe/Razorpay (after GST) | Add live API keys to OpenBao. Test checkout flow. Enable paid plans. | Dev | After GST | BLOCKED | P0
20 | Hire QA intern to execute test cases | Test case register is complete (210+ TCs). QA intern executes and files bugs. Internshala posting ready. | Thiru | Day 7 | PENDING | P1